## Area 100
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 100
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | Company | OEM | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1 | 1 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need cable tray layouts & support details for Mixer MCC Rooms and Mixer Rooms |  | 2023-10-03 | TSI | 09/19/23 - TSI has stated finalize drawings will be provided by the end of the week. TSI to share drawings incomplete with PCE. PCE will review drawigs with their engineering without fabrication until drawings are released for construction. 9/26/23: Anode received, released for construction. Cathode planned for October 6th - top priority for completion. | x
2 | 2 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need BOM of ALL cable tray, strut, rod, etc ordered and timing of when balance of material will arrive onsite |  | 2023-10-03 | TSI | 09/19/23 - Throughout the rest of the week all material for line #1. TSI to share BOM list to Copper Range by EOB today. 9/26/23: BOM received cable tray, strut. Timing for delivery of balance: TBD, order placed. Anode 2nd floor delivered. 1 of 5 delivered. 10/4: Update tomorrow on delivery dates.
3 | 4 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need cable schematics and cable schedules for EMF |  | 2023-09-22 | TSI | 09/19/23 - TSI to upload to Copper Range by end of the week. Closed 9/26
4.1 | 1 | 2023-09-19 |  | RM | PCE |  | Mixing |  | Anode & Cathode | Need cable schematics and cable schedules for Netzsch Mills |  | 2023-10-03 | Netzch Mills | 09/19/23 - Need to review with LG/Ultium. Need to inquire about team members from Netzsch Mills. For construction cable schematics/schedules need to be loaded accordingly. 9/26: Need Netzch contact. IICC to investigate via UC1 10/3: FOB requested, expected by Friday.
5 | 1 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need Field cable schematics and Field cable schedules for ALL Mixers (Anode & Cathode 1-4) |  | 2023-10-03 | TSI | 09/19/23 - Pending complete/certified drawings. TSI to report back by the end of the week. 9/26/23: Waiting on certification from TSI HQ. 10/16 for Line 1. Top Priority. 10/3/23: Still tracking 10/16 delivery or sooner. | x
6 | 1 | 2023-09-19 |  | RM | PCE |  | Mixing |  | Anode & Cathode | Need updated panel/bus schedules for MOD 1-4 |  | 2023-10-03 |  | 09/19/23 - Pull latest utility matrix with Don Jana and Superior Electric. IICC/PCE to follow-up with team members. 9/26/23: Need contact from LG to release…? 10/3: Utility Matrix Available 2.2 or 3.0. IPD support needed, request sent to Jangpill Oh. | x
7 | 2 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | TSI Mixers - Need Material BOM for crates from Korea |  | 2023-09-22 | TSI | 09/19/23 - TSI team members will provide BOM list in english and TSI team members will be checking with PCE all crate deliveries. TSI will provide priority list for all process items. 9/26/23: Available, TSI to upload to CR 9/26 PM. 10/3: TSI to send link
8 | 2 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need Main Mixer Disconnect Switches & Strut Rack |  | 2023-09-30 | TSI | 9/19/2023 - Will be provided as done at UC2. To follow up next week. 9/26: Strut Rack to be shipped from Korea. Switches to be procured locally. PCE to send CAD layout to TSI & p/n.
9 | 1 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need equipment drawings + remote IO panel locations from TSI |  | 2023-10-06 | TSI | 9/19/2023 - TSI to provide drawings by 09/27/23. Posted to Copper Range for record. Need to provide the IO panel naming on the drawings. 9/26: Line 1 drawings to be uploaded 9/27. 10/3/23: Layout received. PCE to review and comment.
10 | 1 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need wire label printer from TSI |  | 2023-10-11 | TSI | 09/19/23 - TSI team members to inquire about the label printer and labels with TSI team at UC2 and will follow up next week. 9/26/23: U2 - TSI proivded printer and labels. TSI to provide further feedback next week. PCE to submit DCR for label approval.
11 | 1 | 2023-09-19 |  | RM | PCE |  | Mixing |  | Anode & Cathode | Need all Bus plugs for Mixer Equipment |  | 2023-09-22 | Superior | 09/19/23 - Superior Electric has procured the bus plugs at their warehouse. PCE and Superior Electric to coordinate deliveries/logistics of the bus plugs. Need to verify fuses were purchased by Superior Electric. 9/26: SE working on lead times and required plugs, fuses + process to monitor usage through job. 10/3: Plugs purchased and local. PCE will have a connex to store plugs after full moblilization including trailers.
12 | 1 | 2023-09-19 |  | RM | PCE |  | Mixing |  | Anode & Cathode | Verify Main Mixer Disconnect & Core Drill Locations (we have a recommendation from U2) |  | 2023-09-22 | PCE/TSI | 09/19/23 - PCE to provide what they utilized at UC2. To review with Don Jana and team members to incorporate drawings. 9/26: Core drill locations sent over. Confirmation needed GM/IICC/TSI. 10/3 - Proposal submitted based on UC2, PCE to send drawing and provide feedback.
13 | 2 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need all vibration sensors, RPM sensors, temperature sensors going in Main Mixer Motor Enclosure |  | 2023-10-31 | TSI | 09/19/23 - Need to provide list and ETA of parts arriving onsite to PCE. TSI to look into providing complete list and to follow up next week. 9/26: RPM & Temp already installed. Vibration sensors to be installed on-site. To be shipped 10/6, arrival date end of October.
14 | 2 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need all VC type disconnect switches for all motors not shipped on skids i.e. Ring Blower Motors, Hydraulic Pump motors, Mazzella Rail etc. |  | TBD | TSI | 09/19/23 - TSI to review internally to verify all items are coming to site. If not, then these items would potentially need to be purchased local to the site. 9/26: Missing VC type disconnect switches to arrive mid December.
15 | 1 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need delivery date for Line 1 MCC Panels |  | 2023-10-10 | TSI | 09/19/23 - TSI has stated that LGENS has requested to modify MCC Panels. MCC Panels will be delayed per TSI to mid-November to ship from Korea. 9/26: Mid December arrival. Need to review schedule impact. 10/3/23: PCE / IICC to review impact on schedule
16 | 4 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | Need cable schedule of pre-run main mixer cables |  | 2023-09-26 | TSI | 09/19/23 - TSI to review internally to verify with their team and report back to the team. 9/26: Closed, TSI reporitng no cable to be run.
17 | 2 | 2023-09-19 |  | RM | PCE |  | Mixing |  | Anode & Cathode | Need Limit switches and dustbin high level switches for DC Towers |  | 2023-09-26 | Ghafari | 09/19/23 - Capture accordingly to submit a DCR to Ghafari for review. . 9/26: GF aware, meeting on 9/29. Update?
18 | 1 | 2023-09-19 |  | RM | PCE |  | Mixing |  | Anode & Cathode | Need circuit requirements / equipment layout for IQC Room |  | TBD | PCE | 09/1923 - May want to capture in our bundle of utilities to handle. Provide DCR for clarification. 9/26 - Don to review and advise.
19 | 3 | 2023-09-19 |  | RM | PCE | TSI | Mixing |  | Anode & Cathode | PCE needs terminals labeled in the touch panels & all RIO panels to be installed on the 2nd floor on Anode & Cathode (this came up at U2 and just trying to get ahead of it if it becomes and issue on U3) |  | TBD | TSI | 09/19/23 - Need panel drawings labled completely from TSI. TSI to review their team members internally and report back to the team. 9/26/23 - Continue to monitor to avoid in future.
20 | 1 | 2023-09-19 |  | JA | IICC | TSI | Mixing |  | Anode & Cathode | Brass Monument Layout for Mixing |  | 2023-10-04 | TSI/IICC | 09/19/23 - R&E will be onsite tomorrow to review layout process. Further review into next week on layout plans. 9/26/23: R&E engaged, brass monuments via R&E planned for next week. Mounting to be discussed with UC2 / BMC 9/27. 10/3: R&E visit complete. Updated drawing. TSI to dimension and approve by 10/4 close of business. TSI to provide back to Korea for approval, latest Friday morning so IICC can re-engage R&I.
21 | 1 | 2023-09-19 |  | JA | IICC | TSI | Mixing |  | Anode & Cathode | Penetrations in Mixing. Need to review and provide drawings. |  | 2023-09-26 | TSI | 09/19/23 - Were all holes cored prior to equipment being set? Need to verify with TSI and provide drawings to crosscheck equipment layouts. 10/3 - Penetration layout available on CR.
22 | 4 | 2023-09-19 |  | JA | IICC | TSI | Mixing |  | Anode & Cathode | Need approval on Mixing Jig |  | 2023-09-22 | TSI | 09/19/23 - IICC to confirm drawings posted to Copper Range are IFC drawings from TSI prior to fabrication. 9/26/23: Complete & Released from TSI
23 | 1 | 2023-09-19 |  | JA | IICC | TSI | Mixing |  | Anode & Cathode | Service Hoist Layout needs to be provided |  | 2023-09-26 | TSI | 09/19/23 - Need to provide hoist layout to confirm abatement locations. 9/26/23 - Layout for hoist as well as complete area 100. BMC to review locations. 3D models to be provided tomorrow - provide Mazzella contact for site visit. 10/3 - Locations uploaded on CR, clash with fire suppression Feedback requested from TSI. Review off-line for next steps.
24 | 1 | 2023-10-02 |  | Kevin Bartos | BMC | TSI | Sus Plate |  | Anode & Cathode | BMC requesting to adapt the Sus Plate layout to reduce the installation complexity. TSI reporting Line 1 can't be changed, Line 2, 3, 4 can be reviewed accordingly. |  | 2023-10-10 | TSI | 10/6 - Updates possible, BMC proposal challenged by lack of material. Line 1 as TSI provides. Updated drawing by 10/6 on what is possible.
| 2 | 2023-10-02 |  | Rob Mard | PCE |  |  |  |  | PID Drawings and List of Field Devices identifying which panels they connect to. |  | 2023-10-31 | TSI | 10/3 - PID uploaded, PCE to review.
25 | 2 | 2023-10-02 |  | Paul Kurtzhals | Conti |  |  |  |  | Conti requesting to Bring in 6 Pack Welding Machines into each Mixing room and on each Floor. Need 460v/100 Amp for Each. 4 total to Start. Is this power available in Building? |  | 2023-10-06 |  | BMC: Need one week to resolve.
27 | 2 | 2003-10-02 |  | Jason Einsporn | PCE |  |  |  |  | 100-amp power back on each floor , located in the middle placed near or on line 3 out of the way of line 1 and 2 for production . |  | 2023-10-06 |  | What would help is to have panel boards strung from main power packs to the contractors laydown and lift charging areas .
28 | 1 | 2023-10-03 |  | Paul Kurtzhals | Conti |  |  |  |  | TSI Drawing index: Is one available? |  | 2023-10-10 | TSI
29 | 1 | 2023-10-03 |  | Paul Kurtzhals | Conti |  |  |  |  | Schedule for Drawing Releases? |  | 2023-10-10 | TSI | Thursday 10/5 follow up meeting 9am (invite sent).
30 | 1 | 2023-10-03 |  | Paul Kurtzhals | Conti |  |  |  |  | Drawings for Pipe Supports in Coater Corridors. When can we expect them? |  | 2023-10-10 | TSI
31 | 2 | 2023-10-03 |  | Paul Kurtzhals | Conti |  |  |  |  | Schedule for Mixing Equipment arrival? | Schedule for Mixing Equipment arrival? | 2023-10-10 | TSI
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Area 200
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 200
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | Company | OEM | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
|  | 2023-10-02 |  | Paul Kurtzhals | Conti |  |  |  |  | Hanger layout Drawings for Cathode and Anode Coater Corridors requested.
|  | 2023-10-02 |  | Paul Kurtzhals | Conti |  |  |  |  | Please provide means to request openings and their location approval in Pre-Cast Wall Separating Mixing and Coater Room for Both Cathode and Anode: Need to run Piping Through This wall From Mixing to Coaters. Information Requested: 1) Point of Contact (Who Approves the Layout) 2) Pre-cast Layout and individual Slab Drawings 3) Areas in Slabs that are off Limits. 4) Who Cuts the Openings?
|  | 2023-10-02 |  | Paul Kurtzhals | Conti | TSI |  |  |  | Please provide other means to Access Model. We cannot extract from Copper Range. At U2, TSI created a Google Drive Account and Supplied Username and Password in order to retrieve Model.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## SRP
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 300
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | Company | OEM | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Area 300
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 300
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | Company | OEM | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Area 400
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 400
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | Company | OEM | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Area 500
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 500
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | Company | OEM | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Miscellaneous
PRIORITY |  |  |  | UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - Miscellaneous
HIGH |  |  | 1
MED |  |  | 2
LOW |  |  | 3
CLOSED |  |  | 4 | [9 empty] | AS OF DATE: | 2023-10-03 18:17
NO. | PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OEM | Contractor | Process Equipment | Process Equipment # | Process Equipment Location | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45