## Area 100
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 100
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS | TSI & LGES Comment (KOR) | TSI & LGES Comment (ENG)
1 | 2023-09-19 |  | PCE | Need BOM of ALL cable tray, strut, rod, etc ordered and timing of when balance of material will arrive onsite |  | 12/26/2023 now 1/12/2024 | TSI | 10/17 - 11/6 material arrival on site. Anode 1F - 11/28 (all four lines for each) Cathode 2F - 12/12 Cathode 1F - 12/19 Update 11/15 on delivery dates improvements, what is planned when, potential partial deliveries. Need countermeasures for late orders. Orders placed 10/23. Need strut and support hardware. TSI to order ASAP. TSI to confirm order date and delivery dates - 11/21 update. Support Hardware Date - 12/11/23 (?) Shipping time 1 day from Tennessee 11/29: Dates provided to PCE 11/22. PCE is re-planning the work and determining the efficiency and time loss. Delay anticipated for MCC rooms. Delay in mixing still being quantified. No improvment offered by TSI. Is it possible for a partial deliveries fittings, accessories...? TSI to confirm delivery of supports (?). On track... Delay anticipated for MCC rooms. Delay in mixing still being quantified. Order deadlines for Line 2 will be determined by SAIL/IICC/PCE to avoid ordering delays in future. 12/12: All lines ordered TSI to provide dates for arrival BOM for LInes 1-4 to be uploaded to CR today.(12/12) 12/19 PCE submitted spreadsheet detailing quantites received of tray and hardware PCE is in dire need of 1/2" threaded rod & hold down clamps. Will arrive 12/21, 22 Additional "RED" items identified 12/21. TSI to provide order & delivery dates. | (11/15) Cable Tray Support 자재(1~4라인분) 현장도착납기 및 BOM List 확인 요청 (Strut, rod...) (※ BOM 전달 완료, Anode 2F Fab in 완료) - Anode 1F - 23.11/28일 (공장도착기준) - Cathode 2F -23.12/12일 (공장도착기준) - Cathode 1F - 23.12/19일 (공장도착기준) - 부분적으로 도착할 수도 있으며, 납기가 미뤄지지 않도록 지속 Tracking 예정 * 원인 : 현지 Loal 업체 (Wesco)에서 구매 예정이 었으나, 현지 업체에서 납기지연됨 (IICC에서 조달하더라도 Wesco에 발주진행되어 납기이슈는 동일현상이며, TSI에서 사전 발주진행하여 현재 일정으로 가능함) * 대응방안 : '23.10월 1~4라인까지 전량 발주 진행했고, 순차적으로 부분입고 진행 예정 (11/22) 소분류 추가 작성하여 일정 공유 완료(11/22, to PCE) (11/27) Cable Tray Support 자재 입고일정리스트 (12/01) 본 일정 Target으로 문제 없이 진행 중 (12/08) 일정 업데이트 (12/19) 일정 업데이트 (1/8) 일정 업데이트 (Hold 내역은 금주 내 발주 예정이며, 입고 일정 기입 예정) | (11/22) Materials categorized and schedule shared to PCE(11/22) (11/27) Material receiving schedule list (12/08) Updated schedule("Area 100_No.2" sheet) (12/19) Updated schedule("Area 100_No.2" sheet) (1/8) Updated schedule("Area 100_No.2" sheet)
4 | 2023-09-19 | 2024-01-09 | PCE | Need delivery date for Line 1 MCC Panels |  | 2023-12-26 | TSI | 09/19/23 - TSI has stated that LGENS has requested to modify MCC Panels. MCC Panels will be delayed per TSI to mid-November to ship from Korea. 9/26: Mid December arrival. Need to review schedule impact. 10/3/23: PCE / IICC to review impact on schedule. 10/10 - Continue to monitor schedule, depends on meeting other committments. 11/6: TSI to re-confirm. 11/14: Status? Shipped 11/1, roughly 45 days (11/16) * LGES requests the logistics team to transport the equipment by 12/1 (11/14) * GM SAIL (Don Jana) confirmed that transportation is necessary by 12/15 All panels arrived 11/27, except console panel. To be confirmed. PCE Install Date? 12/19 - PCE still needs confirmation of EMF panels - PCE & TSI searching. Location sent 12/26. | (11/14) * FOB : 11/1 진행, ROS : 12/1일로 카고리스트 작성, - 미국 항구 도착 (11/14일완료) - 빠른운송 필요시 물류팀에게 협조 요청 필요 (트럭킹 진행요청, LGES) (11/16) * LGES에서 물류팀에 12/1일까지 설비 운송 요청 (11/14) * GM SAIL (Don Jana)가 12/15일까지 운송필요하다고 확인함 (12/01) Console panel은 ROS System container에 실어서 운송 중 (FOB 11/15 완료, 12월 중순 하역 예상) (1/8) ROS System container 도착 완료(12/21) EMF(Electric Magnetic Filter, 자력선별기) panel이 포함된 Container Number 전달 완료(12/21) → 현장 확인 일정 조율중(TSI and PCE) | (11/14) * FOB: 11/1 in progress, ROS: Prepare cargo list 12/1, - Arrival at U.S. port (completed on 11/14) - If fast(urgent) transportation is required, ask for cooperation from the logistics team (trucking request, LGES) (11/16) * LGES requests the logistics team to transport the equipment by 12/1 (11/14) * GM SAIL (Don Jana) confirmed that transportation is necessary by 12/15 (12/01) Console panel : Shipped(11/15), and going to be arrived on site middle of December. (1/8) ROS System containers arrived(12/21) Container Number for EMF(Electric Magnetic Filter) panels shared to PCE(12/21) → scheduling to see on site(TSI and PCE)
2 | 2023-09-19 |  | PCE | Need Limit switches and dustbin high level switches for DC Towers |  | 2023-01-02 | Ghafari | 09/19/23 - Capture accordingly to submit a DCR to Ghafari for review. 9/26: GF aware, meeting on 9/29. Update? 10/10: Roll into Ghafari weekly meeting 10/24 - Meeting, 10/27 will be able to give information to PCE Status:? 11/7 - review Friday 11/10 11/15 DCR review Part of DC Tower RFI package...? Package 30% reviewed today. To be posted by 12/1. Don to post to CR for PCE review. End of December supplier to be nominated. Check CR. Layouts needed, Quincy to follow up.
3 | 2023-09-19 |  | PCE | PCE needs terminals labeled in the touch panels & all RIO panels to be installed on the 2nd floor on Anode & Cathode (this came up at U2 and just trying to get ahead of it if it becomes and issue on U3) |  | 2023-12-26 | TSI | 09/19/23 - Need panel drawings labled completely from TSI. TSI to review their team members internally and report back to the team. 9/26/23 - Continue to monitor to avoid in future. 11/.29: All RIO panels still need to be labeled. PCE reviewed panels this week - not labeled. Support from TSI Needed to label. 12/1 TSI engineer coming to support labels for RIO panels. Target completion by 12/7. (12/01) Name tag : TSI member is putting tags on it.(12/1~). Labeling on-going. Continue to monitor. 1/9/24 - monitor going forward | (11/14) Wire Label Printer 요청 - 23.12월 중순까지 실물 현장도착하여 PCE에 빌려줄 예정 - 구매여부 및 입고여부 확인하여 23.11/15일까지 회신 예정 (11/16) * TSI에서 ~12/15일까지 제공할 예정으로 확인 (12/01) 단자대 Name tag 설치 예정,, 담당자 현장 도착(12/1) 후 작업 중임 | (11/14) Wire Label Printer Request - Scheduled to arrive on site by the middle of 23.December, wil be rented to PCE - Scheduled to reply by 23.11/15 to confirm purchase and stocking status (11/16) * Confirmed to be provided by TSI by ~12/15 (12/01) Name tag : TSI member is putting tags on it.(12/1~)
2 | 2023-10-02 |  | PCE | List of Field Devices identifying which panels they connect to. |  | 2023-12-26 | TSI | 10/3 - PID uploaded, PCE to review. 10/10: Need a list of field devices by skid to be installed by 10/31 Instrument list uploaded on CR. Updated list for Anode uploaded, PCE to review and provide feedback. TSI to provide file path. PCE looking for device numbers to plan term and pull packages. PCE to check ISO's. 10/31 - device list in 3 weeks - 11/21 list 11/7 - TSI had a discussion with PCE regarding to clarify request. 11/21 - draft version sent today, P&ID sent, adding what is in/out TSI is adding more to the list. What has/hasnt been installed. TSI to provide information within a week 11/29: Need to filter list by ship lose, P&ID shows dividing line for what is on/off skid. PCE to review if designation is enough. (12/01) Instrument List : Uploaded on Copper Range(11/28). 12/12: PCE feedback: Incomplete. Yubin to follow up on completing this per PCE. 12/19 - Yubeen from TSI is working on marking up P&IDs to complete the list of field devices. Continue to complete list. 1/9/24 - anode cathode complete by 1/12/24 | (11/22) Instrument List 송부 예정(~11/28, Copper ragne 업로드 예정) (12/01) Instrument List 업로드 완료(11/28) (1/8) I/O 결선 리스트 중 PCE 현장 작업 필요한 항목에 대해 음극만 우선 작성하여 전달 완료(12/22) 양극 작성 후 전달 예정(~1/12) | (11/22) Instrument List : Copper range upload(~11/28) (12/01) Instrument List : Uploaded on Copper Range(11/28) (1/8) I/O connection List needed to installing on site for Anode are shared to PCE(12/22) Preparing for Cathode(TSI, ~1/12)
1 | 2023-10-03 |  | Conti | Schedule for Drawing Releases? |  | 2023-11-28 | TSI | Piping Drawing Release Plan: Support Iso Anode 2F 9/27 9/27 Cathode 2F 10/15 - 10/30 10/15 - 10/30 Anode 1F 10/30 10/20 10/30 - 10/20 Cathode 1F 10/30 - 10/30 10/30 - 10/30 Coater 11/5 11/15 → CAD 2D Layout (~11/28), 3D/ISO(~12/19), Support 2D drawing(~12/22) Pipe Matrix to be reposted today 11/29 (incomplete) Lines 1 & 2 need to be 100% Design Freeze. IICC requesting LG support to enforce this with TSI. Revisions + On Holds + Missing will result in a Line 1 Installation Delay. 22 new drawings uploaded to CR 12/11. Duplication of drawings on CR, no change tracking, revision tracking, or archving. When will TSI be finished updating? Separate Meeting to be organized by TSI: 2pm follow up 12/14. Results: Final drawings due: Anode: 12/16; Cathode: 12/29 Changes after freeze date will be rejected and added to Continuous Improvement work/budget. 12/26: Anode ISO's - released however some still on-hold Cathode ISO's - 12/27 release - still with some on-hold Piping Support - 12/28 release Corridor Layout still open - TSI to provide date. 1/9/24 - on hold pipe will be removed. | (11/14) Wire Label Printer 요청 - 23.12월 중순까지 실물 현장도착하여 PCE에 빌려줄 예정 - 구매여부 및 입고여부 확인하여 23.11/15일까지 회신 예정 (11/16) * TSI에서 ~12/15일까지 제공할 예정으로 확인 (11/22) 원료실, Corridor, 코터 Top/Back (양/음극) → CAD 2D Layout도면 작성(~11/28), 3D/ISO(~12/19), Support 2D도면(~12/22) (12/01) 세정대, 고압세척기, 버퍼, 이송, 공급(코터설비)탱크, 온조기 수정에 따라 CAD 2D Layout 도면 일정 변경(~12/7) 3D/ISO(~12/19), Support 2D도면(~12/22) (12/08) - CAD 2D Layout : Copper Range 업로드 완료(12/7) - 3D/ISO/Support : 음극(~12/16), 양극(~12/29) (12/19) - 3D/ISO/Support : 음극(업로드 완료 : 12/19), 양극(~12/27) (1/8) - 3D/ISO/Support : 양극 업로드 완료(12/27) - CVT Line 3D/ISO 전달 예정(~1/14) | (11/14) Wire Label Printer Request - Scheduled to arrive on site by the middle of 23.December, wil be rented to PCE - Scheduled to reply by 23.11/15 to confirm purchase and stocking status (11/16) * Confirmed to be provided by TSI by ~12/15 (11/22) Drawing release plan : Mixer room, Corridor, Coader Top/Back (Cathode/anode) → CAD 2D Layout (~11/28), 3D/ISO(~12/19), Support 2D drawing(~12/22) (12/08) - CAD 2D Layout : Uploaded on Copper Range (12/7) - 3D/ISO/Support : Anode(~12/16), Cathode(~12/29) (12/19) - 3D/ISO/Support : Anode(Uploaded on Copper Range, 12/19), Cathode(~12/27) (1/8) - 3D/ISO/Support : Cathode(Uploaded on Copper Range, 12/27) - 3D/ISO for CVT line (~1/14)
2 | 2023-10-10 |  | PCE | Need schematics for AC / DC towers |  | 2023-01-09 | Ghafari | Last week of December for supplier decision and schematic availability. Interface meeting btw TSI & Ghafari will be needed. Assumes all AC/DC towers.
2 | 2023-10-13 |  | BMC | Core Holes |  | 2023-12-26 | TSI | 11/21: Three interferences found. DCR submitted. TSI to provide alternative locations. 4th interference found, revised drawing to be released tomorrow. 11/29: Clarifcation of additional 15 inch core holes location in question. --> New DCR to be defined. DCR for 11/21 interferences approved. by TSI. (12/01) TSI will reply about DCR(#15) (~12/4) 15" floor core holes - BMC to approve location and buy off. Timing TBD 12/19: Line 2 Anode/Cathode core hole locations needed. I Line 2 layout - TSI to dimension based on Brass Datum's installed, request and provide date. 12/26 Plan: 1/3 - Receive drawings 1/9 - FMG to drill. | (11/22) 1. 서쪽으로 2inch 이동하여 타공 2. 동쪽으로 2inch 이동하여 타공 3. 서쪽으로 1inch 이동하여 타공 4. 동쪽으로 2inch 이동, 타공 직경 8inch -> 6inch로 변경하여 타공 (11/27) * 수정GAD도면 코퍼레인지 업로드 완료(11/24) 1. 서쪽으로 2Inch 이동하여 타공 2. 동쪽으로 2Inch 이동하여 타공 3. 서쪽으로 1Inch 이동하여 타공 * 수정GAD도면 코퍼레인지 업로드 완료(11/27) 1. 동쪽으로 2inch 이동, 타공 직경 8inch -> 6inch로 변경하여 타공 (12/01) DCR(#15) 회신 예정 (~12/4) (12/08) DCR(#15) 회신 완료(12/5) (1/8) 도면은 기공유 완료 됐었음 | (11/22) * Core holes change Part1. move 2inch to the west → GAD uploaded on copper range(11/24) Part2. move 2inch to the east → GAD uploaded on copper range(11/24) Part3. move 1inch to the west → GAD uploaded on copper range(11/24) Part4. move 2inch and Diameter change(8inch → 6inch) → GAD uploaded on copper range(11/27) (12/01) TSI will reply about DCR(#15) (~12/4) (12/08) TSI replied about DCR(#15).(12/5) (1/8) The Drawings are already shared.
2 | 2023-11-20 |  | PCE | SRP Fiber Material: Has the fiber, converters, fan out kits etc been ordered? Need delivery / timing and cut sheets on all parts ordered |  | 12/26/2023 now 1/20/2024 | TSI | To be clarified PCE & IICC Cathode PLC panel out to SRP PLC panels Will go through profinet - send term locations next week Has a material for this SOW been ordered? Answer next week MEC/TSI review next week on hand-off (12/01) A meeting about communicating between Mixer and SRP will be held on 6th of December.(LG, TSI, MEC) Cable/Tray to be purchased and shppped from Korea. TSI providing material, drawings on Copper Range...Install TBD? Shipping dates to be provided next week (TSI). 12/26: To be checked with HQ. Yubeen to provide dates. 1/9/24 - air freight and here by 1/20 | (12/01) 미국시간 12/6 미팅 예정((TSI, MEC, LGES믹싱설비기술팀) - SRP - Mixer 통신 방법 및 케이블 자재 준비 R&R 협의 (12/08) 미팅 일정 변경(12/6 → 12/12) (12/19) 자재(배관, 서포트, 케이블트레이, 케이블) 준비는 TSI에서 진행함 - 배관, 서프트 이미 현장 도착완료 - 케이클트레이, 케이블 : 발주 진행 중, 일정확인 중 (1/8) - 케이블트레이, 케이블 도착 예상(~1/20) | (12/01) A meeting about communicating between Mixer and SRP will be held on 6th of December.(LG, TSI, MEC) (12/08) Changed meeting schedule (12/6 → 12/12) (12/19) Preparing the materials(Pipe, Pipe support, Cable, Cable Tray) is TSI scope. - Pipe and Pipe Support are on site. - Cable and Cable Tray are on purchasing. (1/8) Cable and Cable Tray will arrive until 1/20
2 | 2023-11-20 |  | PCE | SRP Fiber Run - Are there drawings / schematics / cable schedules available? 2nd floor MCC room out to SRP bldg. |  | 2023-12-26 | TSI | To be clarified PCE & IICC Confirm exact SOW - SRP end TBD John MacLean to follow up with UC2 Execution team. MEC/TSI review next week on hand-off. TSI providing material --> Drawing status? 12/26: To be checked with HQ. Yubeen to provide dates. 1/9/24 - PCE and TSI speaking after whiteboard meeting Wednesday | (11/27) * 광케이블 연결 도면 : System configuration 업로드 * 광케이블 제공 : TSI | (11/27) * Fiber cable connection drawing : Uploaded on the copper ragne (System configuration) * Supplying fiber cables : TSI
1 | 2023-12-01 |  | IICC | Monorail layout for Lines 2, 3, 4 needed, When is material going to be here? |  | 2023-01-09 | TSI / Mazella | Layout requested to continue to progress the abatement process and install monorails earlier on lines 2-4. Line 1 2nd floor released Anode/Cathode. Working on Lines 2-4. Date needed from TSI:? Mazzella to prepare layout for lines 2-4 by 1/9. Anode and Cathode. 1/9/24 - TSI to give us an answer later today | (12/01) #2 Layout 요청(TSI → Mazella) 완료(11/30) (12/19) Mazella 측으로부터 회신 받을 예정(~1/9) (1/8) - #2, #3 Copper Range 업로드 완료(12/29) - #4(1차) Copper Range 업로드 완료(1/8) | (12/01) TSI requested #2 Layout to Mazella(11/30) (12/19) Layout will be shared until '24. 1/9 from Mazella (1/8) - Uploaded : #2(12/29), #3(12/29), #4(Draft, 1/8)
1 | 2023-12-05 |  | PCE | Need installation date for panel designated for IQC Room - Panel PLF6-1-2 |  | 2023-12-26 | Superior | Location changed. Removed, not reinstalled. Superior waiting on change order.
1 | 2023-12-05 |  | PCE | What is the red tag date for the IQC Room? |  | TBD | SAIL/GM | Align with Mixing TBD
4 | 2023-12-05 | 2024-01-09 | PCE | In Utility Matrix, the MCCB for each PD Mixer panel is sized for 500A, but at UC2, it was increased to 600A due to breaker sizing required by code. By the FLA shown in the Utility Matrix, it should be increased to 600A. Need a confirmed Ultility Matrix for Coater Corridor as well. |  | 2023-12-22 | TSI | TSI to double check PCE planning for 600a 500a confirmed as correct, motor spec is lower than received. Reflects UC2 Line 3. Utility matrix going to be re-issued - TSI to re-issue. Due by 12/22. PCE to issue material order by 12/29. 12/26: TSI released and confirmed from LG/ENS to send to LG construction team. | (12/08) * PD Mixer 판넬의 MCCB 는 500A가 맞음. TSI에서 500A로 설치되어 있는지 추가 확인 예정이며, 차단기 산정 근거 전달 예정(~12/12) (12/19) 산출 근거 건설측에 전달 완료 (1/8) - UT Matrix 공유 완료(12/29) | (12/08) * The MCCB for each PD Mixer panel is 500A, not 600A.(TSI will share the reasons.) TSI will check the MCCB on site if that is installed correctly, too. (12/19) UT Matrix is shared to Construction team(LG side). 500A is ok. (1/8) - UT Matrix is shared to PCE(12/29)
4 | 2023-12-12 | 2024-01-09 | PCE | There are discrepancies between the bus schedules and what is needed for install for the High Pressure Cleaners and the Water Heaters - on the bus schedules there are only (4) High Pressure cleaners shown with (6) to install and there are only (8) Water Heaters shown with (12) to install |  | 2023-12-26 | Superior | Superior to update bus schedules.
3 | 2023-12-12 |  | PCE | The CAD file showing the IQC room does not match the actual IQC Room dimensions / layout. We need the CAD file adjusted to reflect the true layout of the IQC Room |  | 2023-12-12 | IPD | Follow up with Quincy on finding support at IPD.
3 |  |  | PCE | Fire Sprinkler Interference - Cathode Cable Tray |  | 2023-12-26 |  | PCE proposal from UC2 to be reviewed after the meeting. TSI to review proposal from PCE 12/13. 1/9/24 - shambaugh to relocate, and PCE to install a cover | (1/8) - 소방배관 위치 수정 + 하부 스프링클러 헤드 커버 설치로 협의 완료(1/3) | (1/8) - Discuss result : Change Fire water pipe position + install cover of sprinkler head (1/3)
4 |  | 2024-01-09 | TSI | Cathode Pre-Mixer 1-3 damaged, to be replaced. FOB end of January out of Korea (TBC by TSI). |  | 2023-12-26 | SAIL | Targeted install date was 1/8-1/12 When will 2-3 be installed? Isolation valves? 1) Need build/ship date from TSI. Mixer and Tank module to ship in April - onsite in June (?) 2) Team to evaluate impact on Line 1 Cathode install (BMC/PCE/Conti M) Line 3 PO done, on-order. TSI to provide more detail on expediting replacment and scope. Ship date for 3-3. Can the replacement be shipped piece meal? Use existing skid as a potential? TSI to provide drawing of 3-3 for comparison.
3 | 2023-12-15 |  | BMC | Missing Gantry Hoist for 1-2, 1-3, 1-4. When will these ship and be on site? Only 1-1 on-site – |  | 2023-12-26 | TSI | Delivery date needed ASAP. Material on-site. Need drawings, install direction and anchors. Is the Mazella beam on-site? | (1/8) Gantry Beam #1-1, #1-2, #1-3, #1-4은 모두 도착해있음 음/양극 1층 Maintenance용 Hoist Beam은 설치 완료 음극 2층 SiO 투입 호퍼 빔은 입고 예정(~1/10) | (1/8) - Gantry Beam for #1-1, #1-2, #1-3, #1-4 were arrived. - Hoist beams for maintenance of Anode(1F)/Cathode(1F) were installed. - Hopper beam(SiO, Anode 2F will arrive (~1/10)
3 | 2023-12-15 |  | BMC | Motor Cover Plate (black & yellow striped floor plate) is slightly too small. The lip of the covers sit on the concrete floor about ½” around the edges. There is enough play in the steel beam supports under the plate that this could potentially fall into the hole if bumped. (permanent floor covering provided by TSI – timing – TBD). Plan needed to address. |  | 2023-01-09 | TSI | TSI to review and provide plan to address. (Note: Issue was noticed on Anode 1-2: we have barricades around this area to keep people off the plate due to this issue.) TSI - Propose to add shims. Looking for more long term solution. 12/26: TSI to provide short term / long term plan of action to address. Field Fix? Re-order in larger size? 1/9/24 - TSI having one last discussion tomorrow and will proceed | (1/8) - TSI Size 확인 완료, 건설 측 Size 확인 중 | (1/8) - Checked size and discussing with Construction team.
4 | 2023-12-15 | 2024-01-09 | BMC | Need updated Platform drawings / install manual. The drawings we have on hand do not match the material on site. |  | 2023-12-26 | TSI | Need updated drawings to match material on-site + installation manuals, torque specifications, etc. | (1/8) Platform 조립도 전달 완료(12/26) 하여 설치 진행 중 | (1/8) Assembly drawing for Platform is shared(12/26) and being installed
4 | 2023-12-19 | 2024-01-09 | PCE | Cathode sprinkler head moves (2x @ E9.5 column 1F) |  | 2023-12-26 | Shambaugh | Awaiting confirmation
4 | 2023-12-19 | 2024-01-09 | PCE | RO skid disconnect / piping install clash. |  | 2023-01-09 | TSI | TSI to propose solution. TSI to mark proposed disconnect location on floor for rewview with PCE.
3 | 2023-12-19 |  | PCE | Confirm PCE to use cable schedule over schematic when there is a discrepancy. When will schematics be updated? |  | 2023-12-26 | TSI | DCR to be issued, TSI to clarify direction to install team. | (1/8) 전장 도면 보다 Cable Schedule에 맞춰 업무 진행 | (1/8) Use cable schedule over schematic
3 | 2023-12-19 |  | PCE | Use of Junction boxes for all PD & BTN mixers. |  | 2023-12-26 | TSI | Direction, layout (SOW) plan requested from TSI. PCE to issue DCR. 1/9/24 - need the full scope of work. Walk down tomorrow morning after whiteboard | (1/8) #1 Junction Box는 특송으로 진행 중(~1/20), #2 이후에는 설치된 채로 운송 예정 | (1/8) #1 Junction box : Shipping(~1/20) (Junction box will be shipped after being installed from #2.)
3 | 2023-12-19 |  | Conti Elec | Coater AC5 panel drives (6) missing - track for future delivery |  | 2023-12-26 | TSI
3 | 2023-12-26 |  | IICC | Pipe Labeling for mechanical install. Who is providing labels? |  | 2023-01-09 | TSI | TSI making the labels. Will provide lead time | (1/8) TSI 에서 제공 예정(현재 제작 중이며, 일정 확인중) | (1/8) TSI is making the label, checking the schedule and will give them.
2 | 2024-01-09 |  | BMC | GAD for Line 2, 3, 4 - Release Dates |  |  | TSI
2 | 2024-01-09 |  | PCE/BMC | Core Holes for lines 2,3,4 |  |  | TSI

## Area 200
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 200
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
1 | 2023-10-02 |  | Paul Kurtzhals | Hanger layout Drawings for Cathode and Anode Coater Corridors requested. |  | 2023-12-26 | TSI | Support 11/5; Iso 11/15 Design Version #28 will be released in 2 weeks. Impact timing TBD! (11/22) Drawing release plan : Mixer room, Corridor, Coader Top/Back (Cathode/anode) → CAD 2D Layout (~11/28), 3D/ISO(~12/19), Support 2D drawing(~12/22) All Coater Corridor 100% on-hold. Delay TBD. Status: Conti to check 12/21 deliveries per TSI email on Copper Range.
3 | 2023-10-16 |  | Brian Klapp | Centerlines for Cathode Line 2 needed, confirm alignment and or additional measures to be taken. Solutions to Coater / Column clash - pit location |  | 2023-12-26 | Daejin / Norris | 11/14 - Jangpill, and construction team to review this further. GM, IPD, Sail team, and LG construction for this discussion Daejin to provide model overlaying coaters (Anode Lines 2 & 4) in building space accounting for all building columns. -> Cathode line 1 by 11/17, rest of the lines by end of next week --> Jangpill & Charlie evaluating column relocation Cathode Lines 2 & 4 (cost and timing). Due: 11/22 11/21 - Daejin to provide answer by Friday. Follow up meeting 11/29, 30 J. Maclean to schedule. (11/20.23) * Cathode line #1 center line 40mm shift layout drawing completed and copper range upload / Provided to Norris (11/16) (11/27.23) * Drawings applied with the line 2~4 avoidance plan To be uploaded copper range today (11/27) No building column move, Daejin updating drawings today for final locations. Follow up meeting to be scheduled - J. Maclean by 12/1. Meeting held. Team is aligned on shifts. Drawings to be updated with dimensions off building columns. (12/04.23) * Cathode #2 Top pit Stage revision drawing Copper range upload completed (12/04) * Cathode/Anode #2 line marking drawing in progress (~12/15) Follow up when drawings released on CR. Line 2 uploaded 12/15 - verify
1 | 2023-11-07 |  | Conti | Cable pull schedules Cable supply inventory |  | 12/26/2023 now 1/12/23 | Wooshin | (11/20.23) * Oven part completed data sharing (11/17) * Top/Back part is working on (11/22.23) * Schedule-Crate material matching results conducted by Cont need to be shared * Wooshin material list sharing completed (11/24) Conti to provide feedback based on inventory status provided feedback on gaps. Wooshin follow up needed. Rev 2 Cable Schedule to be provided by Wooshin - address Conti conerns. 12/1 Escalation Meeting. Wooshin schedule not matching Hirano drawings. 12/5: LG requesting IICC to follow Wooshin direction. IICC requesting Hirano agreement in writing to deviate from Hirano drawings. Hirano drawings will not be updated to reflect Wooshin changes. 12/12: Multiple clarifications ongoing...when will cable pull schedule be frozen? (12/11.23) * Confirm that Hirano agrees to the Wooshin installation guide - If necessary, a mail with the content will be sent Clean Up Pass needed to incorporate all changes. Wooshin date: ? 12/15 Lastest update 12/15 uploaded to Copper Range. 12/19 committed to as Final Date for changes. Need Wooshin feedback for final design freeze. Changes from Hirano submitted 12/19 Wooshin proposes 12/29 for final cable schedule To accelerate, Wooshin will release pull schedule by panel (17 panels AC1:? , AC2: ?...) Changes after freeze date will be rejected and added to Continuous Improvement work/budget. 179 corrections needed in 1 panel
1 | 2023-11-07 |  | Conti | Termination Books - all fall under line item 10 |  | 1/9/2023 now 1/12/23 | Hirano | LG to identify Hirano team for support 11/14 - Wooshin to provide Installation books provided by Hirano on 11/17. Cover in 11/21 meeting with Wooshin. Hirano claims all info with Wooshin. (11/27.23) * Documents sharing completed (11/24) Anode / Cathode sumbitted. Conti Feedback? Escalation meeting needed. Revisit after cable schedule update
2 | 2023-11-09 |  | BMC | Area 200 Anode & Cathode Corridor #1 tank layouts needed |  | 2023-12-26 | TSI | Input for Sus Plate planning TSI reworkng tank and water heater layouts. Two weeks to complete. 12/22 completion target.
4 | 2023-11-10 | 2024-01-11 | Conti elec. | Delivery dates for cables & tray - Anode & Cathode Line 1 |  | 12/26/2023 now 1/29/2023 | Wooshin | 2 containers arrived. Content TBD. Request to move into building. In building, need to inventory. (11/20.23) * Completed move into the factory (located in Cathode No. 2) * Wooshin to check parts (11/27) Packing list provided by Wooshin Status:? Final check of fittings in the ovens. Conti providing feedback Confirm by 12/15 based on oven invetory. Conti checking Ovens this week. Potential High Risk if not part of Oven delivery. Ovens being unpacked, ladder tray, fittings, etc. still TBD. Conti & Wooshin reviewing delivery contents to determine missing parts. Conti only waiting on the ladder tray fittings - 3 or 4 week of Jan
4 | 2023-11-10 | 2024-01-09 | Conti elec. | Cable Tray Layout Drawings Needed |  | 2023-12-26 | Wooshin | Drawings to be released Wed 11/15 (Ovens) - submitted. Top / Back - Released by 11/22 Incl Anode and Cathode Update tomorrow with Wooshin (11/20.23) * Oven part completed data sharing (11/17) * Top/Back part is working on (11/27.23) * Drawing sharing completed Wooshin requesting two weeks to complete Top/Back designs. 12/5: Wooshin communicated "concept only" for tray layout...? Conti to dimension to proceed. Building to current drawing. 12/19: Top and Back cable tray drawings not available. Wooshin to provide ASAP. 12/26: Same status as 12/19. Design complete, checking with OEMs. Plan to finish reviews this week, Wooshin to submit to Copper Range by 1/3.
4 | 2023-11-21 | 2024-01-09 | JEG | JEG kick off, expedite pipe design / install download get JEG mobilized starting 12/4. |  | 2023-12-26 | Joong Wong | Layout/Drawings, BOM, Installation Manuals, Welding Specficiations, Fabrication Sheets. Welding spec to be submitted for approval. IICC to ask JW for approval. JW to approve welding spec. JEG following IPD welding spec
3 | 2023-11-21 |  | IICC | Fire suppression system definition needed. Areas 100-500 requeted from Conti Fire. |  | 2023-12-26 | IICC / Conti | Kick Off 11/27 Conti requesting CAD models and building tie in definition needed. 3 weeks for fabrication needed to start install Conti FP to start with UC2 design. Kick off held, site visit 11/30. Conti working with UC3 models Pre-fab ongoing, will mobilize week of 12/4 Contacts for "rest of plant" needed.
2 | 2023-12-12 |  | Conti elec. | Terminal Boxes needed to address cable layout revisions 1. We need updated drawings showing where these boxes are supposed to be installed. 2. We need the Cable Matrix updated to show cables going from the panels to Terminal boxes. 3. We will need to have the Added Cables from the new Terminal Boxes to the field devices added to the Cable Matrix. 4. Termination info needed. |  | 2023-01-03 | Wooshin | Wooshin to provide material. Quantity: 150+ Need by date:12/26 Status needed by 12/12 COB. 78 sent with Ovens. Wooshin to locate. Remaining terminal boxes to be ordered by Wooshin 12/19: 1-4 Due as part of the final 12/29 submission Wooshin requesting 12/29 + 2-3 days to finalize.
3 | 2023-12-04 |  | Conti elec. | Coater Lights missing - |  | 2023-12-20 | Wooshin | To be delivered to Conti Warehouse by 12/20. Delivery date TBC. 1/9/24 - back order till end of Jan.
1 | 2023-12-15 |  | JEG | Hot Oil Piping Support Design needed to cost and fabricate to address scope gap. Field Order needed |  | 2023-12-26 | Joong Wong / Ghafari / LG | Design needed from Joong Wong.
2 | 2023-12-19 |  | JEG | Identify 1F bridge work durations with and without ovens/blowers installed. Net savings? |  | 2023-01-09 | JEG / Conti E / Conti FP / Allied | To be discussed in Coater team meeting on 12/20. JEG reviewing 10" weld timing and branch piping. 1/9/24 - next Tuesday to provide follow up/answer
3 | 2023-12-19 |  | Conti elec. | e-Stops crate locations to be provided by Hirano |  | 2023-12-26 | Hirano | Hirano follow up requested. Wooshin to follow up with Hirano and provide feedback. Wooshin checking inventory, plan to turnover to Conti 1/5. 1/9/24 - Wooshin has not turned over anything, just has the stands
2 | 2023-12-26 |  | Conti elec. | Need confirmation on the Hirano drawings posted to Copper Range, Is this the final release? Is there another release planned? |  | 2023-12-26 | Hirano | Released for Construction.
3 | 2023-12-21 |  | Joong Wong | JW requesting support for discolored ductwork damaged in shipment. |  | 2023-12-26 | IICC | IICC / subs cannot support - not budgeted for time and/or funding. 1/9/24 - reevaluate this issue
2 | 2023-12-21 |  | IICC | Duct work missing scope - need drawings / installation manuals to evaluate work and timing. |  | 2023-12-26 | Hirano | Hirano to submit ASAP. Mfg drawings available, Hirano to describe install with separate document. Hirano to UC 12/27, UC to IICC 12/28.
4 | 2023-12-21 | 2024-01-09 | GM | Roll Map define work scope, timing, plans to support. |  |  | LG / IICC
4 | 2023-12-21 | 2024-01-09 |  | Avaco Kick Off planned for 12/27 for FA
4 | 2023-12-21 |  | Conti Elec | Panel drawings needed Anode/Cathode |  | 2023-12-26 | Hirano | Part of 12/29 final submission. Follow up early January. Final drawings submitted, date stamped for December '23.
3 | 2023-12-26 |  | IICC | Delivery / Install timing for dust collectors, FFU, EFU |  | 2023-01-09 | Hirano
3 | 2023-12-26 |  | IICC | Pipe Labeling for mechanical install. Who is providing lables? |  | 2023-01-09 | Joong Wong | IICC to follow up with JW. 1/9/24 - DCR sent out, and JW reviewing this currently
4 | 2023-12-26 | 2024-01-09 | Conti elec | Define Roll Press Schedule, List of Contractors, OEMs to start preparations. |  | 2023-01-09 | IICC
3 | 2024-01-09 |  | Conti Elec | Roll Press - conti would like to start pull ahead. Release of equipment schedules
3 | 2024-01-09 |  | AMS | IPD duct work interference. Chase with facility taking a look at it and will get it handled per Joe Arnold
2 | 2024-01-09 |  | Conti Elec | Wooshin wants conti to hold off on tray above ovens

## SRP
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - SRP
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
3 |  |  | SAIL | Latest FOB dates to be communicated, track weekly for updates / changes. |  | 2023-12-12 | MEC | FOB dates received: Mid October (Absorber, Distallation, Reboiler, Module Skid) Tower Internal: Arrived in Lansing 10/23 Control Panel – ASK: early November requested - expedited, early Jan delivery ROS MEC: Middle December FOB - Early Feb ROS - VEC ok with delivery date. (ROS "Plan" per schedule is 1/1/24) Tank – Mid Dec or Jan - ROS Plan...?. MEC procures locally, Jon to clarify ROS dates with MEC. Absorber 11/1 Baltimore USA - ROS Plan: 11/30 Pumps/Distributor/Vacuum - ship date…? Plan ROS: 12/10/23 Towers on-site Line 1: 12/19 Line 2: 1/29 Craine Schedule - VEC to clarify Modules on-site: 12/11 (how are these being off-loaded?) - arriving tarped, will need to be unwrapped to lift and set. Distillation arrived, stays on truck. Absorbers to re-start 12/27, planned arrival in PM. Absorbers arriving 1/29/24 on site
4 |  | 2024-01-09 | VEC | Documentation requirements, reporting, QC (redlines, leak testing, continuity, etc) |  | 2023-11-06 | IICC | TBC
3 |  |  | LGES | Design comparison for MI2 & UC3 designs for NMP circulation system, include level of insulation and gasket specifications. Ultium to evaluate design change request and specify details of change. |  | 2023-01-05 | MEC IICC / VEC | Comparison data sent by 10/20. Need to know the full range of change Eric to organize an off-line meeting to level set and define next steps. Status / Next Steps…? Follow MI2 piping, insulate all electronic components. Heat Trace (?) NMP & Cooling Water Lines, All the tanks. LG asking for same as MI2. Scope to upgrade UC3 is clear. Quotation needed MEC + Install Team. ~ 2 weeks to quote. Follow up mtg MEC & VEC to clarify. 11/7 - VEC providing pricing next Tuesday for all three options 11/13 - ROM estimates received. Next steps? 12/5: Line LIst to be updated and provided by LG including insulation thickness. Electric panels to be added if needed. 3 weeks to quote. --> Complete 12/11. Targeting 1/5 for Quotation.
2 |  |  | VEC | Isolation Valves recommended for a "phased start up". Addition of four valves required. Approval of change and costs needed. |  | 2023-12-26 | Mark / Kevin | IICC to send request to Minkoo to evaluate - complete DCR 002 sent to GM/LG/UC Add to drawings & prepare a cost estimate for material & install. Quote to be prepared. 11/13 - ROM estimates received. Next steps? Quoted - Need FO approval to proceed.
3 |  |  | VEC | Laydown area, additional preparation including gravel install needed. |  | 2023-12-12 | GM / Ultium | 10/31 walk planned. Laydown space south of ring road needs to be prepared. BMC communicating "not in scope". Grade it flat, and that is all at this moment. Coordinate through Alan Plan to complete? 11/7 - Don following up with Alan 12/5 - To be complete by 12/4 Latest - Ring Road option likely plan of record. Quote for matting provided by VEC. Feedback needed.
2 |  |  | VEC | Verify Key Dates ("by others"): Power on to SRP bus Nitrogen System Complete Boiler System Complete Plant NMP Feed Line Water supply to SRP area |  | 2023-12-19 | GM: J. MacLean | 12/26 Planning - for discussion: Power on SRP bus: 3/2/24 Nitrogen system: 4/1/24 (Piping readiness by JEG?) NMP needed: 4/15/24 Boiler System: BMC/JEG planning on 2/22/24. Complete 5/24/24? 1/9/24 - NMP and Nitrogen will get pushed
3 |  |  | VEC | Confirm NMP need date for system commissioning based on RTSO progress Mixing/Coating |  | 2023-12-15 | GM: J. MacLean | Clarification needed. @ RTSO Date: 6/7 (?) Re-evaluate dates and options for provide NMP ahead of RTSO.
|  |  |  | DI Water Pump accessibility. |  | 2023-12-26 | GM: J. MacLean | Reviewing clearance access for maintenance.

## FA
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 300
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS
4 | 2023-11-09 | 2024-01-10 | Conti elec. | Layout of AGV'S Anode and cathode |  | 2023-12-27 | Cowintech | Malyk to follow up with Cowin Tech Need input & coordination from Kiju Still in sourcing at Ultium. No mixing AGV's. in Conti scope. Cowintech equipment, scope of charging to be discussed.
4 | 2023-11-09 | 2024-01-10 | Conti elec. | Layout of AGV's for mixing rooms |  | 2023-12-27 | Cowintech | Malyk to follow up with Cowin Tech Need input & coordination from Kiju Still in sourcing at Ultium. No mixing AGV's. in Conti scope. Cowintech equipment, scope of charging to be discussed. In sourcing through Ultium - no time frame at this moment, much later down the road
3 | 2023-11-09 |  | Conti elec. | Install manuals for All FA equipment |  | 1/3/2024 now 1/17/24 | Cowintech | Cowin Tech to provide, Malyk to follow up. Send links to Dan Hone FA Meeting 12/13 Stockers received. Conveyors needed. (in process). Complete by 1/3. Conveyors 1 & 2 received. 3 & 4 still needed, and missing duct information in the manual. Jan 17th
4 | 2024-01-09 |  | ASI | Overall building and conveyor layout with column numbers. |  | 2023-12-27 | Cowintech | Old versoin on CR. 12/22 last update available on CR. ASI to check.
3 |  |  | ASI | Equipment installation drawings needed. Modified drawings sent, not on CR yet. Drawings to be uploaded today. (using the same VDL centerline) |  | 2023-12-27 | Cowintech | Uploaded. ASI to check. Confirm 100% complete. In process - moving forward right now. Cowintech - 2-3 updated drawings still will be completed 1/15 mezz
4 |  | 2024-01-09 | Conti | Electrical panel locations within Area 100 layout to be re-confirmed. |  | 2023-12-27 | Cowintech | Raw material stocker crane panel moved to oppposite side in UC1, UC2. Panel location is correct per Cowintech
2 | 2024-01-10 |  | Conti elec. | Jumbo Roll Stockers for Area 200 - Manuals, Descriptive material pull sheet |  | 2024-01-17 | Avaco
3 | 2024-01-10 |  | ASI | ASI - Anchors, and Drill. Ordered through Hilti |  |  | Cowintech

## Area 300
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 300
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS

## Area 400
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 400
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS

## Area 500
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - AREA 500
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS

## Miscellaneous
UItium #3 Lansing Battery Plant Process Equipment Installation Project OPEN ISSUE TRACKING MATRIX - Miscellaneous
1
2
3
|  | 4 |  |  |  |  | AS OF DATE: | 2024-01-12 07:15
PRIORITY | DATE ADDED | DATE CLOSED | ADDED BY | OPEN ISSUE | RESOLUTION | DUE DATE | RESPONSIBILITY | COMMENTS